Summary of telephone call between OFE and FSFE, 24th May

Participating: Graham Taylor (OFE), Georg Greve (FSFE), Shane Coughlan (FSFE).

Updates:
- OFE met with Scott Thompson, head of the NOC. Scott is interested in further interaction with FSFE.
- Work with Reinhard Muller regarding the creation of on-line submission and review system for Certified Open is under way.
- There is no new information regarding groupware solutions for managing Certified Open.
- Karl de Vriendt at the Commission informally reviewed Certified Open's definition of an Open Standard and said it is acceptable.
- The minutes of the meeting of the 2nd of May were reviewed and various updates were made.
- OFE and FSFE agreed to split the task of contacting various potential members of the Certified Open Governing council between them (see the minutes of the meeting of the 2nd of May for more details).

Action items:
- Creation of the terms of reference for the Certified Open governing council – (tasked to Shane, FSFE).
- Creation of an overview letter for potential governing council members – (tasked to Shane, FSFE).
- Review of the Certified Open principles of operation – (tasked to Graham, OFE with additional review by Shane, FSFE).
- The Certified Open terms and conditions document needs to be updated – (tasked to OFE).
- Feedback from FSFE legal representatives regarding the MoU needs to be sent to the Certified Open board – (tasked to Georg, FSFE).
- OFE and FSFE arranged to have another telephone meeting on the 1st of June at 16:00.