Project title: Free Open Source Software for SMEs

Project activity:
Terms of Reference and Research Brief:
Policy Recommendation Report (O3/A1)

Brussels, Belgium

The European Commission’s support for the production of this publication does not constitute an endorsement of the contents which reflects the views only of the authors, and the Commission cannot be held responsible for any use which may be made of the information contained therein.

CONTEXT

Grant agreement	2017-1-EL01-KA202-036112
Programme	Erasmus+
Key action	Cooperation for innovation and the exchange of good practices
Action	Strategic Partnerships
Project acronym	FOSS4SMEs
Project title	Free Open Source Software for SMEs
Project starting date	01/10/2017
Project duration	24 months
Project end date	30/09/2019
Project Activity (A) / Intellectual Output (IO) / Multiplier Event (E) / Short-term joint staff training events (C)	O3/A2 – Terms of reference and research brief
Deliverable title	Terms of Reference and Research brief for the Policy Recommendation Report
Nature of deliverable	REPORT?
Dissemination level	CONFIDENTIAL
Due date of deliverable
Produced	P3- OpenForum Europe

Terms of Reference and Policy Brief
Policy Recommendation Report

This document serves as a project plan for drafting the FOSS4SMEs Policy Recommendation.

The Terms of Reference will cover the following aspects to consider:

- The vision, objectives, scope and deliverables
- Stakeholders, authority, roles and responsibilities
- Resource, financial (costs and budgets) and quality plans
- Work breakdown structure and schedule
- Major assumptions and constraints
- Key risk areas
- Project approach or strategy used

1 What
1.1 Vision
The Policy Recommendation Report (hereafter referred to as “the report”) is an integral part of the FOSS4SMEs project without which the FOSS4SMEs projects impact will be severely restricted. Its contents will be designed to support the exploitation of the project results. This means the uptake of the course itself in SMEs, supporting the re-use of the course and/or its parts and support the European policy environment for FOSS.
FOSS awareness and education is the perfect tool to increase the technology competences of European citizens, businesses and the public sector. A priority for the European Union is to increase the digital competence of SMEs, but the role of FOSS has not been adequately acknowledged. FOSS is also a perfect fit for the SMEs, as they usually don’t offer products covering the whole production cycle, making them depend on collaboration with other (SMEs) to link products into a productivity chain. FOSS is conductive to interoperability, linking different products together into a coherent productivity workflow. Aside from the business realities, the collaborative FOSS development and usage environment ensures that users become more than just users, but part of the project – collaborators. Using FOSS leads to authentic collaboration, which teaches much more than a training course could. Understanding a concept on an abstract level is less impactful than seeing it in action and experiencing through own interaction.
Vision
Capacity-building to raise the awareness of policy-makers of the benefits of FOSS uptake in the private and public sector
The training course should therefore be seen as an introduction to FOSS co-creation and collaboration. It is a means to an end, as the course competence, the FOSS business user, is a catalyst for software development collaboration.
Another benefit to the collaborative development method of FOSS is that the freedoms to use, study, share and improve empower citizens, businesses and the public sector to fully understand what the programs they use actually do, e.g. what data it generates and where this data is being sent to. This is a very important aspect of technology sovereignty in the digital age.
To achieve this, the Policy Recommendation Report will provide concrete actions that decision makers at the European level can take to support FOSS uptake.
1.2 Objectives
- Capacity building and raising awareness for the FOSS4SME course for usage by SMEs and re-use in other projects
- Educate about the benefits of FOSS usage for the private sector and citizens
- Educate European citizens and businesses about the collaborative model for technology to increase technology competences and reduce passive use of technology
- Support a free information society through uptake
- Encourage European businesses to be more competitive through FOSS uptake, making businesses more digital
1.3 Scope
The scope for this report will be two-fold. On the one side is European education policy, especially in the area of adult learner skills. Recommendations for this will be important to ensure and accelerate the uptake of the FOSS4SMEs business user model and a policy environment in support of FOSS uptake for SMEs. The report will also recommend actions that create and take advantage of institutional opportunities to use and re-use the course and its contents. The institutions, on a continuing basis, launches initiatives on the intersection of education and technology and these initiatives should take advantage of work already done, including this course, to achieve efficiency gains. In addition, the course will be released under an Open Access license. The project explicitly welcomes a “fork” of the content and to re-use it for another project.
On the other side, European digital policy needs to be addressed to positively impact the European policy environment for FOSS. Here, among others, the areas of innovation, interoperability, procurement, licensing need to be considered specifically. Maybe even more important than recommending specific necessary policy actions will be to adapt the way European institutions consider FOSS. FOSS necessarily belongs to digital policy, which is a policy area that has developed into a horizontal policy field impacting all policy fields. In this, the report will focus on pain points for FOSS adoption, institutional blocks, organisational and legal issues that require action as well as more positive actions, creating a positive policy environment.
1.4 Audience
The Policy Recommendation Report is addressed to policymakers in the European Union institutions, such as the European Commission, the European Parliament and the Council of the European Union. More specifically, the targeted policy makers should work in the policy areas of business, education, technology, procurement and innovation.
There will be abridged versions of the report, extracting a specific part of the Policy Recommendation Report, such as recommendations in education policy. These abridged versions will then be sent to policy makers whose work corresponds to the policy area the abridged report focuses on.
1.5 Deliverables
There are three main deliverables in Output 3, including sub-deliverables:
- O3/A1: This Term of Reference document, including:
  - Terms of reference
  - Objectives
  - Research brief and strategy
  - Separate: Analysis of project results and impact
- O3/A2: Draft report and consultation, including:
  - The draft Policy Recommendation Report
  - Distribution of draft report to stakeholders for review
  - Presentation of the report at multiplier event to collect feedback
  - Peer review by consortium
- O3/A3: Final Policy Recommendation Report
  - The final Policy Recommendation Report
  - Summary report
  - Abridged versions
  - Presentation of final report at final multiplier event
  - Translation of deliverables
2 Who
2.1 Consortium
OFE will lead this activity, with support from all partners. OFE will be responsible for the major planning and coordination work on this specific output as well as the drafting. All partners are expected to support “on-demand” and according to their individual strengths, e.g. good relations to SMEs or relations to FOSS experts. Dlearn will, in addition to this, support OFE with the organisation of the final transnational meeting in Brussels in September 2019.
Dlearn and Atlantis are responsible for the peer review of Output 3, including the preparatory documents, such as this and the Policy Recommendation Report itself.
2.2 Partners
The FOSS4SMEs consortium consists of six organisations from different sectors, such as academia, public policy, business and civil society. Through this, the consortium already has extensive knowledge in different areas and the consortium will take full advantage of the varied knowledge available. There are a number of external partners which will be able to contribute their unique knowledge and expertise and through this, support the quality of the Policy Recommendation Report. External partners will be consulted throughout the process, not only during the dedicated stakeholder consultation.
All consortium partners will contribute to this process by making available their contacts and following up with them. We envision a wide range of external partners to be contacted, such as SMEs, public procurement experts, public officials, FOSS experts, adult learning experts and business representatives.
3 How
3.1 Partners
Each partner has a pre-assigned number days per the budget of the FOSS4SMEs project. Below are detailed each partners’ assigned days for this output. In line with its leading role for this output, OFE has been assigned the most work-days for this activity (48), while most other partners will support with ten work days. Dlearn has been assigned an extra eight days, totalling 18 days, as they support OFE with the preparation and follow up of the fourth transnational meeting in Brussels, which will be held back to back with the final multiplier event in Brussels.
Partner	Output 03
	Managers	Teachers/ Trainers/ Researchers	Technicians	Sum/ output/ partner
ATL	0	5	5	10
DLEARN	0	8	10	18
FSFE	0	5	5	10
SKUNI	0	5	5	10
TU Dublin	0	5	5	10
OFE	3	30	15	48
Sum/output/category	3	58	45	106

3.2 Methodology
To assure the quality and timely delivery, multiple tools will be employed. Firstly, these terms of reference provide an overview of the objectives, deliverables, roles, resources and schedule of the work. Clarity on all of these aspects is important to ensure quality and effectiveness of the work.
The recommendations will be based on a number of different sources. There is established academic and professional research in the area. A literature review of digital policy, educational policy, and FOSS policy will be conducted as a first step. There already exists research on the national level, but less so on the European level. This means that the report will be able to pinpoint specific policy questions which should be answered with a European focus. In addition, experts in the field, as described earlier in section??, will be consulted to identify policy recommendations. This can be done through structured interviews, based on the results of the literature review. The partners inside the consortium will contribute with their knowledge to the Policy Recommendation Report.
4 When
For work to be fit for purpose it is imperative to plan a detailed schedule with responsibilities, supporting roles, start and end date of the task. This schedule is designed to complement the existing project work plan (the MCE), which outlines the major milestones of the project. This schedule will be more detailed than the project work plan and thus act as guiding outline. There will be differences between the project work plan and this work schedule, as some deliverables and actions have earlier end dates. This is to allow flexability for possible delays and ensure an on-time delivery of the main outputs as well as to allow for more time for external consultation and reviews of content, which have shown to be quite time consuming.
The work schedule is annexed to this document as Annex I
5. Risks
A major project involving multiple partners by definition has many risks stemming from e.g. coordination, communication, resources etc. issues. By considering and acknowledging these risks, the consortium can develop actions to mitigate risks and plan actions to respond to risks that have become reality. This approach is in line with P2-Dlearn drafted Quality Plan. The Risk table is Annex II of this document.
Annex I
Output	Description	Leader	Support	Start	End
ToR, PB, TL	Prepare first draft and presentation Terms of Reference (ToR), Policy Brief and timelines	OFE	All	21.01.19	11.03.19
ToR, PB, TL	Feedback on ToR, Policy Brief and timelines	All	OFE	11.03.19	15.03.19
ToR, PB, TL	Finalise and present ToR, Policy Brief and timelines	OFE	All	18.03.19	19.03.19
PR	Prepare first draft analysis of project results and impact	OFE	All	03.03.19	19.03.19
PU	Prepare first draft project uptake impact model	OFE	All	03.03.19	19.03.19
PR+PU	Peer review of analysis of project results and project uptake impact model	DL+ATL	OFE	20.03.19	05.04.19
PRR	Prepare first draft Policy Recommendation Report	OFE	All	20.03.19	14.05.19
PR+PU	Finalise and present project results and project uptake impact model	OFE	All	08.04.19	19.04.19
PRR	Stakeholder consultation of draft Policy Recommendation Report	All	-	15.05.19	07.06.19
PRR	Peer review of draft Policy Recommendation Report	DL+ATL	All	15.05.19	07.06.19
PRR	Compile and review contributions to draft Policy Recommendation Report	OFE	All	10.06.19	18.06.19
PRR	Present draft Policy Recommendation Report at multiplier event for feedback	OFE	-	June 19	June 19
PRR	Finalise Policy Recommendation Report	OFE	All	19.06.19	29.08.19
PRR	Translations	ATL, DLEARN, SKUNI, FSFE		02.09.19	23.09.19
	Fourth transnational meeting in Brussels	OFE	All	24.09.19	25.09.19
PRR + Mul	Presentation at final multiplier event in Brussels	OFE	All	26.09.19	26.09.19

Annex II
Risk	Description	Probability	Impact	Risk response
Lack of understanding in regard to goals	Misunderstandings on the goals and requirements during the preparation phase, such as while drafting this document can lead to an irrelevant work plan and lower quality of the outcomes	Low	High	- Constant communication between team members / - Measures to prevent “siloisation” of information and team members / - Frequent communication with stakeholders and experts / - Peer review of this document by other team members / - Using the collaborative platform “keybase” for all documents, so that all team members have access and are involved / - Ensuring careful drafting of this document
Lack of focus and alignment in regard to goals	Broadening of the scope of the output could lead to resources being redirected to objectives which are less important	Low	High	- Clear drafting of goals and objectives for this output / - Regular reviews during the project, e.g. through calls and peer reviews / - Discussions about refocus of resources during the call, to get opinions of all partners
Lack of stakeholder engagement	Engagement of different types of stakeholders are important for the project (consultation, feedback, dissemination), but these stakeholders have different motivations and goals. Some engagement might be limited	High	High	- Strategic analysis to understand the needs and interests of stakeholders / - Developing incentives to increase attractiveness for stakeholders / - Enlarging the group to compensate for drop-outs / - Contact stakeholders the organisations are involved with / - Encourage open communication about level or resources and motivation available to the stakeholder
Not meeting project timetable	Delays of outputs which impact delivery of another output or the whole output	Medium	Medium	- Planning with generous buffers with an understanding that finishing tasks often take longer than initially planned and this should be expected / - Involving the other team members when a delay occurs to increase manpower
Changes in project team	Unforeseen changes in the composition of the project team (illness, maternity/paternity, exit) can lead to resource and expertise gaps	Low	Low	- Each organisation has a number of employees available to take work over / - Each organisation has institutionalised knowledge available / - Substitutes are named to take over
Lack of accessible information	Some information may be inaccessible or not readily accessible. Resources required to access information could be higher than anticipated. This would reduce the quality of the output.	Low	Medium	- The partner organisations are well connected within their field and therefore possess contacts to gain access to information or find alternatives / - Partners are from a diverse set of countries, making information from different countries and in different languages available / - Extensive research will be performed to identify sources of information
Lack of insight about influencing factors outside the immediate scope of the project	We may incur the risk of making policy recommendations that are incompatible – or even conflict – with related pieces of legislation.	Low	Medium	- Organisations within the consortium focus on policy and are aware of policy developments so adjustments are possible / - There will be a reduced output of new policy on the European level due to European elections in 2019 / - Consultations with external stakeholder, also in policy maker circles
Change of the environment and resulting requirements on the project	The FOSS, education and general technology environment may change so that recommendations are less relevant, do not serve the priorities or are not needed	Low	Medium	- Need for digital skills will likely not change in the short or medium term / - FOSS as an appropriate solution for digital skills will likely remain, as it is well aligned with the policy environment, asking for sovereign and collaborative solutions / - The FOSS community is active for over 50 years in some shape and therefore its longevity and continued relevance is proven