FOSS4SMEs – MINUTES of telco in Framatalk 17.12.2018

Participants: / Katerina / Galia (until 12:41 CET) / Jonas & Björn / Francesco / Brian / Sivan

Writing of Minutes
FSFE would be normally responsible to take minutes, but Galia anticipated that she will have to leave early. For this reason FSFE and OFE switched and Sivan took notes for this call.
https://docs.google.com/spreadsheets/d/1G8vxEfkwPfUx4DvcCurBDk9F4W0jYETdF5xgfI-gseY/edit#gid=0

Dissemination
Galia supports Max on dissemination tasks assigned to FSFE and gave an overview of dissemination activities. Galia (as already indicated in her last e-mail before the telco) created new files and uploaded them to the keybase (K:\team\foss4smes\1. Management\Dissemination templates and guidelines) on:
- Tips for social media
- Event form, which should be used when partners attend an event. This document is important for reporting and should always be used when attending an event
- How to Facebook and Twitter  mainly for Katerina, who is administrating all accounts

Galia will send an additional email later.
Katerina asked partners to review the files and give feedback if necessary.
Stakeholders matrix: Please fill it out here K:\team\foss4smes\1. Management\Dissemination tables
Checklists by FSFE: Katerina informed participants that Max will provide the team with a list on important information for dissemination, but this could be discussed since he was not on the call.
Exploitation Plan (A13): Is needed, but could not be discussed since Max was not on the call.
2nd Newsletter: Please fill out your texts here:
https://docs.google.com/document/d/1U_pQ6H5vCYsAF7Ge4WWo9zB1m_XDld2vgsy9p4d81lI/edit

Agenda Dublin Meeting
Katerina sent around the preliminary agenda, which is available under this link: https://docs.google.com/document/d/1D9PuUDPpiWa99QrrMluix_DD4xYKGGM91yvPDtDds40/edit
Katerina asked partners, especially those having to present during the meeting, to provide feedback on the agenda. Presenters need to send their presentations to Katerina before the meeting. During the first day, in each session a specific partner will record content for the course, while the thematic sessions are ongoing. There are going to be 3 types of videos: 1. A welcome video in our native language, 2. A summary video of our unit and 3. A video with main statements for beginners and experts.
Brian informed that the second day is planned as a backup in case re-recordings are needed and asked the partners to record their native-language introduction during those sessions. DIT is currently trying to identify essential content that would be good for dialogue for the video and will update partners later.
Jonas suggested that there should be two recordings per lesson where one is aimed at novices in the topic and one at advanced users. DIT is working on final confirmation of the rooms used for the meeting.

O2/A1 Training content (Leader: DIT)
Katerina reminded partners that she sent around a table today detailing the dates of submissions of deliverables and the reviews already performed by SKUNI and DIT. Current progress of each partner was discussed. FSFE has not provided any results – Max is missing/Galia had no update.

O2/A1 Partners	1st submission	Update after Review from SKUNI	Update after proofreading from DIT	Peer Review by OFE and FSFE	Final update from each partner
ATL - Unit 1	29.11.	13.12.
OFE - Unit 2.1 and 2.2.	03.12.	12.12.
Dlearn - Unti 2.3 and 2.4.	14.09.	14.12. (12:04h)	14.12. (19:14)
Dit - Unit 3	12.12.		-
Skovde - Unit 4	30.11.	-	17.12.
FSFE - Unit 5

Katerina reminded everyone that the peer review is under the responsibility of OFE and FSFE. Katerina informed the group that no peer review should happen until all units have been provided by all partners and she will then inform OFE and FSFE, so that they can conduct the peer review.
[At this point Galia left the call]
Brian added that as soon as the content is on the learning platform, the links and duplications will become much clearer. DIT will provide guidelines on how to write a script for recording before the Dublin meeting and information on the timeline concerning the creation of videos. Katerina reminded DIT of the O2_Training Plan for the course that they need to provide.
Brian replied that they will look at the learning platform.
login data for the learning platform (available in K:\team\foss4smes\2. Implementation\Outputs\Output 2\A3 Distance Learning Platform):
user: atl / pass: kusWQP%2_H
user: dit / pass: eJQ6h=NZXm
user: skuni / pass: f4&Kf^25cm
user: dlearn / pass: BHtrAd*3rq
user: ofe / pass: cVG&hg*9qp
user: fsfe / pass: ZwhM&7yfjw

1 User account for testing
User: testacc
Pass: Testacc1!

O2/A2 - Translations
Katerina recalled that all translations should have been provided by end of December, but this deadline will not be met due to delays. She stated that there is a need to start process of O2/A2 (translations) and asked partners to prepare themselves for the process based on the budgets provided in the proposal. Should anyone has questions, they can contact ATL.

##### To-do list

Action required	Partner	Deadline
O2_Training Plan for the course	DIT	ASAP
Prepare reviewed Unit 1-5 (with images and assessment exercises) taking into consideration the SKUNI and DIT feedback.	ALL	ASAP
Texts for 2nd Newsletter	ALL	ASAP
Translation of units into national languages	ALL	January
2nd newsletter sent	ATL	31.12.18
Stakeholders matrix table: Please fill it out here K:\team\foss4smes\1. Management\Dissemination	ALL	Before M18
Exploitation Plan (A13)	FSFE	ASAP
Dissemination Checklist	FSFE	ASAP
Project newsletters: German translation missing. Add it here: https://docs.google.com/spreadsheets/d/1-mDxEqX0gWLshzZjpkZaF-1krBx7T3D-Utc31oQhZlo/edit#gid=1684811769	FSFE	ASAP
Provide guidelines on script-development for the video recording at Dublin meeting	DIT	ASAP
Perform peer review of training content O2/A1	OFE & FSFE	Start when all content is ready
Send presentations to be held in Dublin to Katerina	All presenters	11.01.19